Statement of Work (SoW)

Knowledge Fabric - Scope of Work

Prepared by:

Submitted to:

Submitted on

Aug 19th, 2026

SoW Number: 19082026_v1.0

www.QualiZeal.com

Corporate Headquarters

QualiZeal Inc., a Delaware corporation with offices at 9901 Valley Ranch Pkwy E., Ste. 2037, Irving, Texas 75063.

Global Delivery Center

iLabs Centre, Block B, 2nd and 3rd Floor

Software units Layout, Madhapur,

Hyderabad, Telangana- 500081

- Table of Contents

1	Engagement Overview	3

2	Scope and Deliverables	3

2.1	In Scope	3

2.2	Out of Scope	4

3	Delivery Approach	4

3.1	Proposed Solution	4

3.2	Phase Plan with Milestones & High-level Activities	5

3.3	Detailed List of activities & deliverables at each sprint:	6

3.4	Technology Stack	8

3.5	Success Criteria	8

3.6	Team composition	9

3.7	Escalation Matrix	9

4	Commercial and Financial Aspects	10

4.1	Commercial Details	10

4.2	Payment Terms	10

5	Assumptions	10

5.1	Project Requirement Management:	10

5.2	Tools, Documentation, and Software Licenses:	11

5.3	Project Communication and Escalation:	11

5.4	Change Management:	12

5.5	Work Compliance	12

6	Signatures	12

Statement of Work (SoW)

This Statement of Work (“SoW”) is executed between Nova Biomedical (“Nova”) and QualiZeal Inc. (“QualiZeal”), effective as of August 19th, 2026 (the “Effective Date”), and is subject to the Master Services Agreement, by and between Nova Biomedical and QualiZeal (the “MSA”) dated March 1st, 2026. In the event of any conflict between the terms and conditions of this SOW and the terms and conditions of the MSA, the terms of the MSA shall control to the extent of that conflict, unless otherwise explicitly stated herein.

# Engagement Overview

QualiZeal is engaged by Nova Biomedical to deliver a governed Product Knowledge Fabric that houses Instructions for Use (“IFU”) and related product knowledge, enabling natural language questions to be answered over approved product content with citations and source traceability.

The Knowledge Fabric is deployed in Nova's AWS environment, authenticates through Microsoft Entra ID, and uses Amazon’s Bedrock routing and model selection to produce grounded answers.

- Key Business Objectives:

- Nova’s teams will be provided with a Nova-branded, enterprise fabric for internal use to product knowledge (“Knowledge Fabric”), with answers traceable back to the source document.

- The Knowledge Fabric will continuously refresh as source documents are added, changed, removed, superseded, or archived.

- Reduce compliance risk. Every answer is grounded in the current approved IFU, cutting the risk of employees acting on outdated or conflicting product guidance.

- Save time. One natural-language interface replaces manual searching across manuals, bulletins, and FAQs.

- Control cost as usage scales. Usage and cost telemetry give Nova visibility to manage AI spend as adoption grows.

# Scope and Deliverables

## In Scope

This SOW covers a working Product Knowledge Fabric deployed in the Nova-provided AWS environment, including content ingestion and version governance, grounded answering with citations, role-based access, multilingual support, and telemetry.

- Ingestion of approved Nova content into Amazon S3, processed through an event-driven pipeline.

- Metadata derivation and version ranking, with conflicting or ambiguous versions routed to a curator review queue for resolution within the application.

- Knowledge base build and incremental synchronization using Embedded Models from embedded models from Amazon Bedrock.

- Grounded answering: filtered hybrid retrieval, a grounding check on the generated response, source citations, and a confidence indication returned with every answer.

- Clarification behavior: where grounding is insufficient, or the question is ambiguous, the platform asks a targeted follow-up question and re-runs retrieval instead of returning a bare refusal.

- Custom web application providing the chat interface, the curator queue, and the administrator views.

- Role-based access for user, curator, and administrator roles, federated from Microsoft Entra ID through Amazon Cognito and enforced on the API.

- Support for English, Spanish, and French across the interface, the question, and the generated answer.

- Telemetry instrumented with OpenTelemetry in Python, and dashboards covering usage, input and output tokens, cost, and answer-quality indicators.

- Deployment into the Nova-provided AWS environment (Development and Production) using Terraform, with CI/CD pipelines in Nova-owned repositories.

- Documentation and structured knowledge transfer to the Nova team at the close of the engagement.

## Out of Scope

- Languages other than English, Spanish, and French.

- Multistep and conditional reasoning. Band C questions as defined in Section 3.3.4, being comparative, conditional or multi-hop questions that require a planning step and several dependent retrievals. These are characterised and measured during this engagement and proposed for delivery under a separate Statement of Work.

- Interpretation of image content. Answers synthesised from a diagram or image where no supporting text exists, extraction from scanned documents that carry no extractable text layer, and video content. The multimodal boundary in scope is set out in Section 3.3.5.

- Retraining or fine-tuning of models. All generation, embedding and reranking uses Amazon Bedrock foundation models as provided.

- Authoring, correction or remediation of Nova source content. QualiZeal surfaces version conflicts and content gaps through the curator queue and the dashboards; resolution of the underlying content remains with Nova.

- Ongoing operation, support or managed service following the acceptance and handover milestone.

- Anything not mentioned above is considered out of scope

# Delivery Approach

## Proposed Solution

The proposed solution has 6 key components spanning the content, answering, and access and telemetry layers.

| Key Components | Activities |
| --- | --- |
| Content Intake Pipeline | - Ingest approved content into Amazon S3 - Event-driven intake through EventBridge and SQS - Extraction and metadata derivation through AWS Step Functions |
| Version Governance & Curator Queue | - Current and superseded status maintained per document - Conflicting or ambiguous versions routed to a review queue - Curator resolution performed within the application |
| Knowledge Base & Retrieval | - Amazon Bedrock Knowledge Bases with Titan Embeddings V2 - Incremental synchronization from the curated content store - Filtered hybrid retrieval with reranking |
| Grounded Answering | - Grounding check on the generated response - Source citations and confidence indication returned with the answer - Clarify-back flow where context is insufficient |
| Access, Roles & Web Application | - Nova-branded chat, curator queue and administrator views - Entra ID sign-in federated through Amazon Cognito - Role-based access enforced on the API |
| Telemetry & Dashboards | - OpenTelemetry instrumentation in Python - Input and output token counts, cost, and latency captured per request - Usage, cost, and quality dashboards |

## Milestones & High-level Activities

The engagement runs for 18 weeks covering discovery, design, implementation, evaluation and handover, delivered across five phases. A further 2 weeks is recommended ahead of Week 1 for pre-kick-off activities such as onboarding and provisioning of environment access.

Week numbering. All weeks referenced in this Statement of Work are relative. Week 1 begins on the first working day after QualiZeal team onboarding is complete and the AWS, Amazon Bedrock and Microsoft Entra ID access listed in Section 5 has been provided. Where onboarding or access is delayed, the timeline shifts by the equivalent duration, and the parties will mutually agree the adjusted dates.

| # | Phase | Duration | High-level Activities | Milestone |
| --- | --- | --- | --- | --- |
| 1 | Discovery & Solution Architecture | Weeks 1–3 | Scope confirmation, content and metadata review, role definitions, solution architecture, security approach, and resolution of the four complexity areas listed in Section 3.3.5 | Architecture Sign-off |
| 2 | Foundations, Access & Early Trial | Weeks 4–7 | AWS environment baseline through Terraform, repositories and CI/CD, application shell, seed corpus trial with grounded answers, Entra ID and Amazon Cognito federation | Seed Corpus Trial Live |
| 3 | Content Ingestion & Version Governance | Weeks 8–12 | Automated intake, extraction and metadata derivation, version ranking, curator queue, knowledge base build and incremental synchronisation | Governed Corpus in the Knowledge Base |
| 4 | Grounded Answering & Experience | Weeks 13–17 | Filtered hybrid retrieval and reranking, grounding check, citations and confidence, clarify-back, Nova-branded application, multilingual support, telemetry and dashboards | Grounded, Cited Answering |
| 5 | Evaluation, Acceptance & Handover | Weeks 18–20 | Evaluation against the agreed criteria, hardening, Production deployment, user acceptance testing, documentation and knowledge transfer | Acceptance & Go-Live |

Note: The phase-level activities and deliverables set out below may change based on the outcome of the Discovery & Solution Architecture phase, subject to mutual agreement between the Nova and QualiZeal teams. The milestone at the end of Phase 2 has been brought forward relative to a conventional plan so that Nova subject matter experts can begin using the platform on real Nova content from Week 6, rather than waiting for the full ingestion pipeline.

## Incremental Delivery Plan and Deliverable Mapping

### How this plan is structured

The five phases above define the contractual milestones. This section sets out how the work inside those phases reaches Nova, and what Nova can expect to see at each point. It is a delivery view rather than a sprint plan: the intent is that Nova never waits more than three weeks to see working software, and that every item listed in Section 2.1 has an identifiable point at which it first becomes demonstrable and a later point at which it is complete.

The engagement is organised into ten increments. Each increment closes with a demonstration on the Nova AWS environment using Nova content. Three principles govern the sequencing:

- Architecture and feasibility first. The first two weeks produce no software. They resolve the architecture and the four areas of technical uncertainty set out in Section 3.3.5, because decisions taken there determine the cost of everything that follows.

- A thin vertical slice before breadth. A narrow but complete path from question to cited answer is built early over a small, manually curated set of Nova documents, before the automated ingestion pipeline exists. This proves the answering path and opens the Nova feedback loop from Week 6 instead of Week 17.

- Depth added in named layers. Ingestion breadth, version governance, answer quality and the full experience are then layered onto that working path in sequence, each with its own demonstration.

Increments INC-1, INC-3 and INC-5 span a phase boundary. This is deliberate: environment provisioning and identity federation are started in parallel with the closing activities of the preceding phase, and that parallelism is what makes the Week 6 trial achievable.

### Increment ladder and demonstration cadence

| Ref | Wks | Ph. | What Nova sees at the close of the increment | Nova involvement required |
| --- | --- | --- | --- | --- |
| INC-0 Architecture & Feasibility | W1–2 | 1 | Walkthrough session, no software. Target architecture and environment topology; draft metadata and version rule set; query complexity bands defined; multimodal handling boundary proposed; evaluation and acceptance approach; findings from the four complexity spikes. | Architecture and security review participants; sample documents for each document type in scope |
| INC-1 Environment & Application Foundation | W3–4 | 1–2 | Development environment provisioned through Terraform in the Nova AWS account; CI/CD pipeline running from the Nova-owned repository; API service and Nova-branded application shell deployed; OpenTelemetry traces visible end to end. | AWS and repository access confirmed; Amazon Bedrock model access enabled in the agreed region |
| INC-2 Seed Corpus Trial | W5–6 | 2 | First working question-to-answer path. A curated seed set of approved Nova documents is loaded, indexed and queryable. Answers return with source citations resolving to the correct document and section. Nominated Nova subject matter experts are given hands-on access and the feedback loop opens. | Seed document set approved for use; 3 to 5 subject matter experts nominated for hands-on trial and structured feedback |
| INC-3 Identity & Role Enforcement | W7–8 | 2–3 | Microsoft Entra ID sign-in federated through Amazon Cognito; user, curator and administrator roles resolved from Entra ID groups and enforced on the API; the seed corpus trial moves behind real Nova identity with role-based navigation. | Entra ID application registration, group definitions and federation approvals; test accounts for each of the three roles |
| INC-4 Automated Ingestion at Scale | W9–11 | 3 | Event-driven intake running on real Nova exports: Amazon S3 to Amazon EventBridge to Amazon SQS to AWS Step Functions. Text and table extraction, metadata derivation, and incremental synchronisation into the knowledge base, demonstrated by adding and re-processing documents live in the session. | Production-representative content export and the agreed export mechanism; confirmation of derived metadata attributes |
| INC-5 Version Governance & Curator Queue | W12–13 | 3–4 | Current and superseded status maintained per document against the agreed rule set; the authoritative source determination visible on each answer; conflicting and ambiguous versions routed to the curator review queue; a curator resolves a conflict in the application and the knowledge base re-synchronises. | Curator role holders identified; version rule set formally signed off; a deliberately conflicting document pair provided for the demonstration |
| INC-6 Answer Quality Depth | W14–15 | 4 | Filtered hybrid retrieval with reranking; grounding check applied to the generated response; confidence indication returned with each answer; clarify-back flow replacing bare refusals. Measured results reported for query Bands A and B against the Nova-approved evaluation set. | Subject matter experts to author and adjudicate the evaluation question set (Band A and Band B) |
| INC-7 Full Experience & Telemetry | W16–17 | 4 | Nova-branded chat with citation display and conversation history; English, Spanish and French across the interface, the question and the answer; administrator configuration and per-role usage limits; usage, token, cost and quality dashboards reporting on live trial traffic. | Brand assets and interface terminology; Spanish and French reviewers; agreement on dashboard audience and per-role usage limits |
| INC-8 Evaluation & Production | W18–19 | 5 | Formal evaluation readout against the agreed acceptance criteria, reported per query band; findings addressed and performance tuning completed; security review and hardening closed; Production environment provisioned through Terraform and the platform deployed. | Security review participation and sign-off; Production environment and approvals; acceptance criteria confirmed |
| INC-9 Acceptance & Handover | W20 | 5 | User acceptance testing supported and signed off; documentation package delivered; source code and Terraform definitions in Nova-owned repositories; knowledge transfer sessions completed with the Nova team. | User acceptance testing participants; knowledge transfer attendees; acceptance sign-off |

Demonstration cadence. Demonstrations fall at the close of Weeks 2, 4, 6, 8, 11, 13, 15, 17, 19 and 20. Each is a working session on the Nova environment, not a slide review. Feedback raised in a demonstration is triaged with Nova and either absorbed into the next increment or, where it changes scope, handled through the change management process in Section 5.4.

### Deliverable mapping to increments

The table below maps each item of scope committed in Section 2.1 to the increment in which it first becomes demonstrable and the increment in which it is complete.

| Committed scope item (Section 2.1) | First demonstrable | Complete | Milestone accepted under |
| --- | --- | --- | --- |
| Ingestion of approved Nova content into Amazon S3 through an event-driven pipeline | INC-2 (W6, manual seed load) | INC-4 (W11) | Phase 3 |
| Metadata derivation and version ranking | INC-2 (W6, minimal metadata) | INC-5 (W13) | Phase 3 |
| Conflicting or ambiguous versions routed to a curator review queue and resolved in the application | INC-5 (W13) | INC-5 (W13) | Phase 3 |
| Knowledge base build and incremental synchronisation using Amazon Bedrock embedding models | INC-2 (W6, full rebuild) | INC-4 (W11, incremental) | Phase 3 |
| Grounded answering: filtered hybrid retrieval, grounding check, source citations and confidence indication | INC-2 (W6, baseline retrieval and citations) | INC-6 (W15) | Phase 4 |
| Clarification behaviour in place of a bare refusal | INC-6 (W15) | INC-6 (W15) | Phase 4 |
| Custom web application providing chat, curator queue and administrator views | INC-1 (W4, shell) | INC-7 (W17) | Phase 4 |
| Role-based access for user, curator and administrator roles, federated from Microsoft Entra ID through Amazon Cognito and enforced on the API | INC-3 (W8) | INC-3 (W8) | Phase 2 |
| Support for English, Spanish and French across the interface, the question and the answer | INC-7 (W17) | INC-7 (W17) | Phase 4 |
| Telemetry instrumented with OpenTelemetry, and usage, token, cost and quality dashboards | INC-1 (W4, instrumentation) | INC-7 (W17, dashboards) | Phase 4 |
| Deployment into the Nova-provided AWS environment using Terraform, with CI/CD in Nova-owned repositories | INC-1 (W4, Development) | INC-8 (W19, Production) | Phase 5 |
| Documentation and structured knowledge transfer | INC-9 (W20) | INC-9 (W20) | Phase 5 |

### Query complexity bands

Answer quality cannot be assessed, or accepted, without agreeing what class of question is being asked. The bands below are proposed at the start of the engagement and confirmed during Discovery against a Nova-authored question set. Acceptance thresholds are reported separately for each band in Section 3.5.

| Band | Definition | Illustrative question | Status under this SoW |
| --- | --- | --- | --- |
| A Direct | A single fact retrieved from a single section of a single approved document. One retrieval, direct extraction, no synthesis. | What is the storage temperature for a given reagent? | In scope. Highest accuracy threshold. |
| B Procedural | An ordered procedure or a synthesis across multiple sections of one document or one product family, including answers that reference a figure or a table. | What are the steps to run a calibration on a given analyser, and which figure shows the port? | In scope. |
| C Complex | Comparative, conditional or multi-hop reasoning across documents, product lines or document versions, where the answer requires a plan, several dependent retrievals and conditional logic. | For a given sample condition on Model X, which protocol applies, and how does it differ from the equivalent protocol on Model Y? | Not in scope under this SoW. Characterised, measured and quantified during this engagement; delivery proposed under a separate Statement of Work. |

Band C is deliberately excluded. Multistep and conditional reasoning requires an orchestration layer, a planner, step-level grounding and a materially larger evaluation surface. Including it here would place the largest source of cost and schedule uncertainty inside a fixed-bid commitment. QualiZeal will instead classify the Band C questions encountered during the trial, size the work, and present it to Nova as a costed follow-on so that the decision is taken on evidence from Nova’s own content.

### Multimodal and device-usage content

A significant proportion of Instructions for Use content is carried in figures, diagrams and tables rather than prose, and a common class of question is scenario-driven: how a device is used, and which procedure applies in a given situation. The boundary for this SoW is as follows.

- In scope: Text extraction; table extraction with table-grounded answers; detection of figures and diagrams, with their captions, labels and surrounding procedural text indexed; and citations that resolve to the specific figure, page and document version so that the user is taken directly to the relevant visual.

- Not in scope: Interpretation of image content where no supporting text exists, answers synthesised from a diagram alone, extraction from scanned documents without an extractable text layer, and video content.

The proportion of in-scope content that carries an extractable text layer is confirmed against Nova sample documents during INC-0. Where that assessment shows a material volume of image-only content, the options and their cost implications will be presented to Nova at the Architecture Sign-off milestone rather than absorbed silently.

### Complexity track and decision gates

Four areas have been identified by the QualiZeal architecture team as carrying above-average technical uncertainty. Each is run as a named investigation with a fixed decision gate, so that the associated design choice is made early and visibly rather than discovered late in build.

| Ref | Area | Question the investigation must answer | Decision gate | Accountable |
| --- | --- | --- | --- | --- |
| CX-1 | AWS deployment and environment topology | Networking, private connectivity and organisational policy constraints in the Nova AWS account; Amazon Bedrock service and model enablement in the agreed region; the Terraform module structure and state backend; and the Development to Production promotion path. | W3 Architecture Sign-off | Cloud Engineer with AI Architect |
| CX-2 | Data versioning, authoritative source and continuous refresh | The precedence rules that determine which document version is authoritative; how supersession, withdrawal and archival propagate to the knowledge base; how re-indexing is triggered and bounded on continuous refresh; and which cases are decidable by rule versus routed to a curator. | W3 Rule set drafted W13 Rule set signed off | Data Engineer with AI Architect |
| CX-3 | Query complexity banding and model routing | Confirmation of the Band A, B and C definitions against a Nova-authored question set; which Amazon Bedrock model tier serves each band; and the cost and latency profile per band that the dashboards will report. | W3 Bands confirmed W15 Thresholds met | AI/ML Engineer 1 with AI Architect |
| CX-4 | Multimodal and device-usage scenarios | The proportion of in-scope content carrying an extractable text layer; figure and table extraction accuracy on Nova samples; and the figure-citation approach that answers scenario-driven questions without image interpretation. | W5 Boundary confirmed | AI/ML Engineer 1 with Data Engineer |

Complexity reserve. A reserve of effort is held within the team allocation in Section 3.6 and released by the AI Architect against these four gates. Where an investigation concludes that the work is materially larger than assumed, QualiZeal will raise it at the corresponding gate with options and impact, so that Nova can decide between absorbing it within the increment sequence, deferring it, or handling it through the change management process in Section 5.4.

## Technology Stack

The stack is confined to Amazon Web Services managed services, Amazon Bedrock, and permissively licensed open-source components. Two constraints govern the selection: no model inference or content processing occurs outside the Nova AWS boundary, and no component is introduced that couples the solution to a commercial vendor beyond the approved AWS and Amazon Bedrock patterns.

| Layer | Component | Licensing and commercial basis | Status |
| --- | --- | --- | --- |
| Application | Python; FastAPI on Amazon ECS Fargate; React served through Amazon CloudFront and Amazon S3 | Open source, permissive (PSF, MIT, BSD). AWS consumption borne by Nova. | Approved |
| Model inference | Amazon Bedrock for model invocation; Amazon Bedrock Guardrails for the grounding check | AWS service consumption within the Nova account. No separate software licence. | Approved |
| Retrieval | Amazon Bedrock Knowledge Bases with Amazon Titan Text Embeddings V2 | AWS service consumption within the Nova account. No separate software licence. | Approved |
| Ingestion | Amazon S3, Amazon EventBridge, Amazon SQS and AWS Step Functions | AWS service consumption within the Nova account. | Approved |
| State and queue | Amazon DynamoDB for the curator review queue | AWS service consumption within the Nova account. | Approved |
| Identity | Microsoft Entra ID federated through Amazon Cognito | Existing Nova Microsoft licensing. Amazon Cognito consumption within the Nova account. | Approved |
| Observability | OpenTelemetry (Python) instrumentation; Amazon CloudWatch; Amazon Athena over Amazon S3 for audit and BI export | OpenTelemetry is Apache 2.0. AWS service consumption within the Nova account. | Approved |
| Delivery | Terraform for infrastructure as code; GitHub Actions in Nova-owned repositories | Terraform is used under its published licence terms for internal infrastructure provisioning. GitHub Actions consumption under existing Nova GitHub entitlement. | Approved, subject to Nova confirming its Terraform licensing position at INC-0 |
| LLM observability (optional) | Langfuse, self-hosted within the Nova AWS account | The Langfuse core is MIT licensed and self-hostable without usage limits. Enterprise modules — including audit logging, data retention policies and project-level role-based access control — require a paid commercial licence key. Self-hosting also introduces a ClickHouse, PostgreSQL and Redis footprint in the Nova account. | Not adopted by default. See note below. |

Note on LLM observability tooling. The observability requirement in this SoW — request-level tracing, input and output token counts, cost, latency and answer-quality indicators — is met by the OpenTelemetry, Amazon CloudWatch and Amazon Athena path already listed above. That path introduces no additional licence, no additional vendor and no additional data store, and keeps all telemetry inside the Nova AWS boundary. Langfuse is recorded here as an option should Nova want a dedicated prompt and trace management interface. QualiZeal draws attention to the fact that audit logging and data retention policies, which are commonly required in a regulated environment, fall within the paid Enterprise modules rather than the MIT-licensed core. Any adoption would therefore be subject to Nova open-source approval, a security review, and a decision on the associated infrastructure and licence cost, none of which is included in the pricing under this SoW.

Note on model providers. All generation, embedding and reranking is performed through Amazon Bedrock within the Nova AWS account. No third-party model endpoint outside that boundary is used, and no Nova content is transmitted to a model provider outside it. Where a stronger or a cheaper model is required for a particular query band, that is handled by model tier selection within Amazon Bedrock rather than by introducing an external provider.

## Success Criteria

Acceptance is assessed against the criteria below, measured on a Nova-approved evaluation set authored by Nova subject matter experts during Discovery and frozen before the evaluation in INC-8. Functional criteria are assessed as met or not met. Quality criteria are reported separately for query Band A and query Band B, as defined in Section 3.3.4.

Functional criteria

- Approved Nova content is ingested through the event-driven pipeline, with metadata derived and current or superseded status maintained per document.

- Conflicting or ambiguous versions are routed to the curator review queue and can be resolved within the application, with the knowledge base re-synchronising on resolution.

- Questions are answered from approved Nova content, with source citations and a confidence indication shown with each answer.

- Where grounding is insufficient or the question is ambiguous, the platform asks a targeted clarifying question rather than returning a bare refusal.

- Answers are available in English, Spanish and French across the interface, the question and the generated answer.

- Access is governed through Microsoft Entra ID, with user, curator and administrator roles enforced on the API.

- Telemetry is captured for every request, and usage, token, cost and answer-quality information is available on the dashboards.

- The platform is deployed in the Nova-provided AWS environment through Terraform, with source code and infrastructure definitions in Nova-owned repositories.

- Documentation is delivered and knowledge transfer to the Nova team is completed.

Quality criteria

| Measure | Band A | Band B | Basis of measurement |
| --- | --- | --- | --- |
| Groundedness — the answer is fully supported by the cited sources | 95% | 90% | Adjudicated by Nova subject matter experts on the frozen evaluation set |
| Citation correctness — every citation resolves to the correct document, version and section | 95% | 90% | Adjudicated by Nova subject matter experts on the frozen evaluation set |
| Version correctness — the answer is drawn from the current approved version and not a superseded one | 98% | 98% | Deterministic metadata filtering, verified against the curated version state |
| Correct handling of out-of-corpus questions — clarification or a grounded refusal rather than an unsupported answer | 90% | 90% | Measured on a set of deliberately out-of-corpus questions supplied by Nova |
| Response latency, 95th percentile | 8 seconds | 15 seconds | Measured from the telemetry captured on the Development environment under trial load |

Note: The threshold values above are the values proposed by QualiZeal. They are confirmed, and adjusted if required, at the Architecture Sign-off milestone once the Nova evaluation set has been authored and the characteristics of the content are understood. Band C questions, as defined in Section 3.3.4, are excluded from acceptance measurement under this SoW.

## Team Composition and Resource Deployment

### Role charter

| Role | No. | Primary accountability | Increments owned |
| --- | --- | --- | --- |
| Program Manager | 1 | Plan, cadence and reporting; demonstration scheduling; dependency and risk tracking with the Nova single point of contact; change management administration. | All (QualiZeal investment) |
| AI Architect | 1 | Solution and security architecture; the four complexity investigations and their decision gates; retrieval, grounding and evaluation design; release of the complexity reserve; technical assurance at each demonstration. | INC-0; assurance across all |
| AI/ML Engineer 1 Retrieval & Answering | 1 | Retrieval and reranking; grounding check and citation handling; confidence indication; clarify-back flow; query band routing and model tier selection; multimodal investigation. | INC-2, INC-6; contributes CX-3, CX-4 |
| AI/ML Engineer 2 Ingestion & Governance | 1 | Extraction and metadata derivation logic; version ranking implementation; curator queue behaviour and resolution workflow; knowledge base build and incremental synchronisation. | INC-4, INC-5 |
| AI/ML Engineer 3 Application & Evaluation | 1 | API service and the Nova-branded application; chat, curator and administrator views; multilingual enablement; evaluation harness, dashboards and the reporting of quality measures. | INC-1, INC-7; supports INC-8 |
| Data Engineer | 1 | Content intake pipeline; document and metadata modelling; authoritative source and continuous refresh design; table and figure extraction quality; content profiling against Nova samples. | INC-4; contributes CX-2, CX-4 |
| Cloud Engineer | 1 | Terraform modules and state; Development and Production environment provisioning; CI/CD pipelines; Microsoft Entra ID and Amazon Cognito federation; security hardening and the Production promotion. | INC-1, INC-3, INC-8; owns CX-1 |

### Allocation profile, ramp-up and ramp-down

Allocation is shaped to the work rather than held flat across the engagement. The profile below shows the planned allocation of each role across the increment windows. The Program Manager is a QualiZeal investment and is not billed under this SoW.

| Role | W1–2 | W3–4 | W5–6 | W7–8 | W9–11 | W12–13 | W14–15 | W16–17 | W18–19 | W20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AI Architect | 100% | 50% | 50% | 50% | 30% | 50% | 50% | 30% | 50% | 60% |
| AI/ML Engineer 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| AI/ML Engineer 2 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 50% |
| AI/ML Engineer 3 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| Data Engineer | 50% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 50% | 30% |
| Cloud Engineer | 100% | 100% | 80% | 60% | 60% | 50% | 50% | 80% | 100% | 80% |
| Program Manager | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% |

Ramp-up. QualiZeal requires 2 weeks’ notice from the date of signature to board the team. The AI Architect, Cloud Engineer and AI/ML Engineer 1 are engaged at full allocation from Week 1, because the architecture decisions and the environment investigation determine the shape of everything that follows. AI/ML Engineers 2 and 3 and the Data Engineer join at partial allocation in Weeks 1 to 2 to absorb context, and move to full allocation from Week 3 when build starts.

Ramp-down. The Cloud Engineer steps down from Week 5 once the Development environment and CI/CD are stable, and returns to full allocation for Weeks 18 to 19 for hardening and the Production promotion. The Data Engineer steps down from Week 14, once version governance is complete, and holds a reduced allocation through acceptance to support evaluation findings. AI/ML Engineer 2 steps down from Week 18. The AI Architect returns to a higher allocation for acceptance and handover. QualiZeal will confirm each step-down point to Nova 30 days in advance, in line with the notice period in Section 4.2, and the Weeks 18 to 20 profile will be confirmed at the INC-6 demonstration in Week 15.

Continuity and complexity reserve. The AI Architect and AI/ML Engineer 1 are engaged across the full 20 weeks so that no phase transition depends on a single handover. Any replacement of a team member carries a one-week overlap at QualiZeal’s cost. The difference between this shaped profile and a flat full-team allocation is retained as the complexity reserve described in Section 3.3.5, and is released by the AI Architect against the CX-1 to CX-4 decision gates. It is not released for scope beyond that committed in Section 2.1.

Working model. The team operates from offshore with a daily overlap into US Eastern hours, extended during demonstration weeks and during the acceptance period. Demonstrations are scheduled within the overlap window. A single QualiZeal point of contact mirrors the Nova single point of contact required under Section 5.3.

## Escalation Matrix

QualiZeal agrees to work collaboratively with Nova to resolve any issues that may arise during the engagement in a mutually agreeable and beneficial manner.

For this purpose, an escalation matrix shall be established with the following hierarchy of contacts:

- Level I: The first point of contact for any issues will be the assigned Delivery Director of the project.

- Level II: If the issue cannot be resolved at the Delivery Director level, it can be escalated to the SVP of Client Success.

- Level III: If the SVP of Client Success is unable to resolve the issue, it can be escalated to the Head of India Operations.

| Escalation Level | Name | Designation | Email / Contact Number |
| --- | --- | --- | --- |
| Level I | Rasool Shaik | Delivery Lead | Rasool.shaik@qualizeal.com |
| Level II | Sanjay Aloor | Client Success | sanjay.aloor@qualizeal.com |
| Level III | Kote Bipilli | BU Head | kote@qualizeal.com |

# Commercial and Financial Aspects

## Commercial Details

The table below provides the resource allocation across the project duration in a Fixed Bid model.

| Role | Number | Allocation | Duration (weeks) |
| --- | --- | --- | --- |
| AI Architect | 1 | 50% | 20 |
| AI/ML Engineer | 3 | 100% | 20 |
| Data Engineer | 1 | 100% | 20 |
| Cloud Engineer | 1 | 100% | 20 |

Note on allocation. The allocation shown above is the average allocation of each role across the 20-week engagement. The planned week-by-week deployment of each role, including the ramp-up and ramp-down points, is set out in Section 3.6.

Note: Program Manager are QualiZeal investment added to the team to ensure collaboration and communication with Nova team.

Total cost of the services for this SoW is $

## Payment Terms

- Net Payment Terms: 30 days

- The above prices do not include any taxes and duties.

- QualiZeal will require 2 weeks’ notice from the date of signature to board the team and 30 days' written notice to ramp down the resources.

- The payment terms for the SoW do not include the cost of tools and licensing, and such expenses are not a part of the above pricing mentioned in the SoW.

- Travel, Accommodation, and Expenses of QualiZeal resources to the client location will be billed at present (with prior client approvals).

# Assumptions

## Project Requirement Management:

- Nova will provide the AWS environment for both Development and Production, together with the required service enablement, including Amazon Bedrock model access in the agreed region, on or before the project start date.

- Nova will provide the QualiZeal team with the necessary access to the AWS environment,

- Nova will provide the Microsoft Entra ID application registration, the group definitions, and the approvals required to federate Entra ID with Amazon Cognito.

- Nova will provide representative sample documents for each document type in scope during the Discovery phase.

- Any organizational policy, networking or security constraints applicable to the Nova AWS environment will be disclosed by Nova in advance and supported through the engagement.

- Nova will provide timely access to logs, telemetry and environments.

- Nova will nominate subject matter experts for content review, evaluation and acceptance testing, and will make them available at the points indicated in the phase plan.

- Source documents in scope are expected to carry an extractable text layer. The proportion of Nova content meeting this condition is confirmed against sample documents during Increment INC-0, and the multimodal boundary set out in Section 3.3.5 applies.

- The languages supported under this SoW are English, Spanish, and French.

- Nova will provide the necessary support and assistance required to complete the testing activities on time.

- Nova will provide feedback and approval within 48 hours upon receiving the deliverables; if no feedback is received within 5 working days, then the deliverables will be deemed accepted.

## Tools, Documentation, and Software Licenses:

- AWS infrastructure, AWS consumption and Amazon Bedrock model usage will be provided and borne by Nova within the Nova AWS environment and are not included in the pricing under this SoW.

- QualiZeal will provide a system with a minimum configuration of 8 GB RAM, Windows 11, and a Core i3 processor for development and testing, and arrange and bill any additional equipment expenses to the client as per actuals for higher system configurations.

- The project team will have access to all necessary tools and software licenses required to perform the development and testing activities.

- Nova will provide the current architecture documents, content and system access, and the necessary support and assistance required to complete the development activities on time.

- QualiZeal will need the below tools and services to be enabled, or access provided within the Nova environment for successful execution of the Deliverables:

  - AWS account access for Development and Production environments

  - Amazon Bedrock model access, Amazon Bedrock Knowledge Bases and Amazon Bedrock Guardrails

  - Amazon S3, Amazon EventBridge, Amazon SQS, AWS Step Functions, Amazon DynamoDB, Amazon ECS Fargate, Amazon CloudFront and Amazon Athena

  - Microsoft Entra ID application registration and Amazon Cognito

  - Nova-owned source repositories with GitHub Actions

  - Terraform state backend within the Nova AWS environment

## Project Communication and Escalation:

- Nova will assign a single point of contact (POC) throughout the engagement who will act as the communication and escalation point for the QualiZeal team.

## Change Management:

- Changes to the project scope, timelines, or Deliverables will be communicated and managed through a formal change management process and any additional costs incurred due to the delay shall be borne by the party responsible for the delay.

- QualiZeal will not be held responsible for delays caused by the Nova’s failure to provide necessary inputs or meet their obligations under the SOW.

- Nova acknowledges that any delays caused by external factors beyond the control of the team, such as infrastructure or system availability, may impact the project timelines.

- QualiZeal will collaborate with the Nova team to identify and mitigate any dependencies or risks that may impact the remaining activities; however, if there is a delay from QualiZeal in achieving milestones, an invoice shall be raised accordingly after the Deliverable is provided to Nova, and QualiZeal will bear responsibility for such delay.

## Work Compliance

- All work performed by QualiZeal shall be in accordance with the scope defined in this SOW.

- Resources assigned under this SOW are expected to work from offshore with flexibility to overlap hours with US(EST) based on project needs or critical phases.

# Signatures

IN WITNESS WHEREOF, the parties have caused this Statement of Work (SoW) to be executed by their duly authorized representatives as of the date written below:

| Nova Biomedical |  |  | QualiZeal Inc |  |
| --- | --- | --- | --- | --- |
| Signature: |  |  | Signature: |  |
| Name: |  |  | Name: | Kalyan Konda |
| Title: |  |  | Title: | CEO |
| Date: |  |  | Date: |  |

(End of Document)