## Slide 1
SWA CARGO TECHNOLOGY · REVISED POC PLAN
Governed AI-assisted delivery
for Cargo, built on Kiro CLI
Revised for a fast outcome — a lean architecture, clear gates and loops, and a 5-week plan
GOAL Show that AI-assisted delivery can move faster while meeting Cargo’s engineering standards
PRIORITY 1
Rate Calculator
Core flow, built end to end and running on AWS dev
PRIORITY 2
Test automation
Playwright tests generated from approved stories
TEAM
Architect + AI engineer
Cargo time: repo walkthroughs and approvals only
PLAN
5 weeks
Dates set once the team and access are confirmed
Prashobh — AI Architect, QualiZeal AI Center of Excellence (CoE) · Draft v0.3 for discussion
AI-DLC: AI-Driven Development Life Cycle · AWS: Amazon Web Services · CLI: command-line interface · POC: proof of concept · UI: user interface · VPN: virtual private network

## Slide 2
LEAN ARCHITECTURE
Four agents, essential guardrails, nothing extra
Cut to what the two POCs need — everything else is deferred, not dropped
INPUTS
Jira stories
Confluence specs
Rate Calculator repo
Playwright repo
KIRO CLI WORKSPACE · CARGO GROUP
Guardrails
Per-agent permissions
Blocking safety checks
Validated hand-offs
Four specialist agents
Story
Build
Test
Review
Design sits inside the Build agent’s plan; hand-offs are simple files — no coordinator needed
Knowledge
Cargo standards
for the two POCs
AWS AI-DLC
practices
Repo maps
for both repos
OUTPUTS
Reviewed merge request
Tests + traceability
Running on AWS dev
Evidence: AI vs manual
OBSERVABILITY every agent action logged · every approval recorded with its reason · weekly scorecard
DEFERRED TO PHASE 2 coordinator agent · separate design and release agents · pipeline-triggered agent runs · dashboards · more tech stacks
QualiZeal AI CoE · SWA Cargo · Governed AI-assisted delivery on Kiro CLI · Draft for discussion
2 / 5

## Slide 3
WORKFLOW · GATES AND LOOPS
Where people decide, and where agents retry
Fast mode keeps three gates for the POC; any gate can be split back out if Cargo wants more control
1 Understand
Story agent
stories + acceptance criteria
2 Design & plan
Build agent
design, build plan, test plan
3 Build
Build agent
code, build, lint, unit tests
4 Test
Test agent
contract + Playwright tests
5 Review
Review agent
standards, security, quality
Merge and deploy to dev
a person merges
A
B
C
failing tests or review findings go back to Build — max 3 rounds, then a person decides
asks questions until the story is clear
fixes its own build and lint errors, max 3
= a person approves
= agent retries
FAST MODE recommended for the 5-week POC
A
Scope
B
Design + plan
C
Review + merge
Three stops instead of six — guardrails, logging and evidence stay the same
FULL MODE when this scales beyond the POC
Scope
Design
Build plan
Test plan
Review
Release
Six gates, one per decision — switched on without changing the agents
PRIORITY 1 Rate Calculator runs all five steps PRIORITY 2 Test automation starts at step 4 with approved stories
QualiZeal AI CoE · SWA Cargo · Governed AI-assisted delivery on Kiro CLI · Draft for discussion
3 / 5

## Slide 4
TIMELINE
5 weeks, with the Rate Calculator first
Assumes 1 architect + 1 AI engineer. Week-wise only — dates are set once the AI engineer and access are confirmed.
Foundation: agents + guardrails
Priority 1 · Rate Calculator
Priority 2 · Test automation
WEEK 1
Set up and discover
Access, Kiro workspace, guardrails
Rate Calculator and Playwright repo walkthroughs
Scope cuts and success measures agreed
Scope agreed
WEEK 2
Agents ready
Story, Build, Test and Review agents live
Dry run on one real Cargo story
Rate Calculator stories and design approved
Agents ready
WEEK 3
Build the Rate Calculator
UI component and pricing integration
Unit and contract tests, mocks where needed
Review loop until findings clear
Code reviewed
WEEK 4
Rate Calculator on AWS dev
Pipeline and deployment to AWS dev
Playwright framework mapped
Test plans approved from stories
Live on AWS dev
WEEK 5
Test automation + results
Playwright tests generated and run
Traceability and coverage summary
AI vs manual evidence, phase-2 plan
Demo + results
Architect architecture, guardrails, Story + Review agents, approvals
AI engineer Build and Test agents, Rate Calculator build, Playwright tests
QualiZeal AI CoE · SWA Cargo · Governed AI-assisted delivery on Kiro CLI · Draft for discussion
4 / 5

## Slide 5
SCOPE AND NEXT STEPS
What we cut for speed — and what we need to start
Cut for the POC — deferred, not dropped
Agents: six roles + coordinator → four roles
Approval gates: six → three (fast mode)
Rate Calculator: core flow and key error states; mocks where services aren’t ready
Test automation: a focused set of approved stories
Pipeline-triggered agent runs and dashboards move to phase 2
To start week 1
1
AI engineer confirmed — Veena and Kanchan
2
Rate Calculator repo and walkthrough — David
3
Playwright repo link — Thirumagal
4
Access laptop, VPN, GitLab, Jira, AWS dev, Kiro Pro
5
Approver one Cargo approver for the three gates
SUCCESS Rate Calculator running on AWS dev and Playwright tests from approved stories — with evidence of AI-assisted vs manual effort
QualiZeal AI CoE · SWA Cargo · Governed AI-assisted delivery on Kiro CLI · Draft for discussion
5 / 5